Comprehensive Assessment Report of Climate Change Impacts in Maryland (Update)

Production Schedule (Draft)

- March 2026

Below is a proposed 15-month production schedule for producing the updated assessment report. This timeline follows the standard workflow used in major climate assessments (e.g., IPCC, National Climate Assessment, state climate assessments) and includes four major phases:

- Planning and scoping

- Writing and analysis

- Review and revision

- Production and publication

## Phase 1 — Project Launch and Scoping

Months 1–2

Goals:

- Define scope and structure

- Recruit author teams

- Confirm datasets and modeling approaches

Outputs:

- Final report outline

- Author teams established

- Data sources confirmed

# Phase 2 — Research and Chapter Drafting

Months 3–6

Goals:

- Conduct analysis

- Draft chapter content

- Produce initial figures and maps

Outputs:

- First draft of all chapters

- Preliminary figures and maps

Typical products produced during this phase:

- climate trend figures

- sea-level rise maps

- hydrology analyses

- emissions inventories

# Phase 3 — Internal Scientific Review

Months 7–8

Goals:

- Improve scientific rigor

- Ensure consistency across chapters

Outputs:

- Revised chapter drafts

- Updated figures

Reviewers may include:

- Academic experts

- NOAA scientists

- Maryland agency experts

# Phase 4 — Report Integration and Design

Months 9–10

Goals:

- Integrate chapters

- finalize graphics

- produce layout

Outputs:

- Final report manuscript

- polished figures

- executive summary

Typical outputs:

- infographics

- climate maps

- conceptual diagrams

# Phase 5 — External Peer Review

Months 11–12

Goals:

- Independent scientific evaluation

- Stakeholder feedback

Outputs:

- Final revised chapters

- documented review responses

Reviewers may include:

- NOAA

- NASA

- USGS

- academic experts

- Chesapeake Bay Program scientists

# Phase 6 — Publication and Release

Month 13-15

Goals:

- publish report

- communicate results

Outputs:

- published report

- press release

- public briefing